## Sheet1
Submission Date
2013-02-15 | Overview of Project and Target Audience | Identify and describe User Stories (1-2 Lines each) and main acceptance criteria | Prioritise Stories | Estimate time | Scope – Group User Stories into each Iteration | Technical options – Comparative Analysis and justification of chosen technologies | Release Plan
2013-03-01 | Define application Architecture | Develop Skeleton System | Database Schema | 1 Page of System and User Stories | Class Diagram | Review of Iteration 1 |  |  | Story ID: 1 - Log In | Story ID: 2 - Generate Forms | Story ID: 6 - Account Creation | Story ID: 3 - Select Input Type
2013-03-14 | User Stories to be added | Class Design | Database Design | Interaction and State Diagrams as appropriate | Tests | Application Code | Integration | Review | Story ID: 8 - Mobile Forms | Story ID: 4 - Table Exports | Story ID: 7 - Public URLs | Implement Error Logging
2013-04-05 | User Stories to be added | Class Design | Database Design | Interaction and State Diagrams as appropriate | Tests | Application Code | Integration | Review | Story ID: 9 - Oauth | Story ID: 5 - Admin Access | Story ID: 9 - Statistics
2013-04-19 | User Stories to be added | Class Design | Database Design | Interaction and State Diagrams as appropriate | Tests | Application Code | Integration | Review | Story ID: 10 - Payment
2013-05-01 | User Stories to be added | Class Design | Database Design | Interaction and State Diagrams as appropriate | Tests | Application Code | Integration | Review | Configure Server (Azure)